## Release#1
Day | Planned | Consumed | Team Availability |  |  |  | Deliverable | % Completed | Comments
1 | 36 | 36 | 70 |  |  |  | CRS | 100%
2 | 42 | 40 |  |  |  |  | SIQ | 100%
3 | 48 | 44 |  |  |  |  | PMP | 100%
4 | 54 | 50 |  |  |  |  | Risk sheet | 100%
5 | 60 | 54 |  |  |  |  | SRS | 100%
6 | 66 | 66 |  |  |  |  | CMP | 100%
Risks
ID | Topic | Probability | Impact | Description | Handling | Actions
Risk_001 | Lack of experience | 5 | 5 | Not all team have computer engineering background which might reduce output efficiency and quality | Avoid | Prioritize crash courses and training sessions for the team
Risk_002 | Team communication issues | 1 | 3 | Team memebers might face internet connection issues as most of the work and meetings will be done online | Mitigate | Team can utilize coworking spaces for internet connection or ensure all team members have stable internet connection
Risk_003 | Tools knowledge risks | 3 | 4 | Not all team members have used tools important for the project such as jira,github and other technical tools | Mitigate | Sharing knowledge among team members and take courses if necessary
Risk_004 | Tools licence risks | 2 | 2 | Some important tools might need licence to use which might delay work quality | Avoid | Use alternative high quality free tools available
Risk_005 | Members availability | 3 | 5 | Team memebers might not be available due to sickness or personal issues | Mitigate | Team members should know each other's task progress and ensure work transparency and have alternative plans to compensate for other members being unavailable
Risk_006 | Customer communication risks | 5 | 4 | Customer meets with team members only once a week which affects constant feedback and consultation | Accept | Before each sprint, team members should have all questions ready and after the sprint all questions should be answered
Risk_007 | Technical debt risks | 5 | 5 | taking the easy way during SDLC might cause increase in rework cost | Avoid | Conduct rigorous peer reviews and ensure each step is done efficiently before moving to the next step
Issues
ID | Initiator | Probability | Impact | Description | Handling | Actions
Issue_001 | Exams and other cources | 4 | 4 | Team is commited to projects,exams and other courses | Mitigate | Distribute tasks among teams based on previous technical backgrounds to increase productivity and conduct daily meetings to monitor progress