## Release#1
Day | Planned | Consumed | Team Availability |  |  |  | Deliverable | % Completed | Comments
1 | 36 | 36 | 70 |  |  |  | CRS | 100%
2 | 42 | 40 |  |  |  |  | SIQ | 100%
3 | 48 | 44 |  |  |  |  | PMP | 100%
4 | 54 | 50 |  |  |  |  | Risk sheet | 100%
5 | 60 | 54 |  |  |  |  | SRS | 100%
6 | 66 | 66 |  |  |  |  | CMP | 100%
Risks
ID | Topic | Probability | Impact | Description | Handling | Actions
Risk_001 | Lack of experience | 5 | 5 | Not all team have computer engineering background which might reduce output efficiency and quality | Avoid | Prioritize crash courses and training sessions for the team
Risk_002 | Team communication issues | 1 | 3 | Team memebers might face internet connection issues as most of the work and meetings will be done online | Mitigate | Team can utilize coworking spaces for internet connection or ensure all team members have stable internet connection
Risk_003 | Tools knowledge risks | 3 | 4 | Not all team members have used tools important for the project such as jira,github and other technical tools | Mitigate | Sharing knowledge among team members and take courses if necessary
Risk_004 | Tools licence risks | 2 | 2 | Some important tools might need licence to use which might delay work quality | Avoid | Use alternative high quality free tools available
Risk_005 | Members availability | 3 | 5 | Team memebers might not be available due to sickness or personal issues | Mitigate | Team members should know each other's task progress and ensure work transparency and have alternative plans to compensate for other members being unavailable
Risk_006 | Customer communication risks | 5 | 4 | Customer meets with team members only once a week which affects constant feedback and consultation | Accept | Before each sprint, team members should have all questions ready and after the sprint all questions should be answered
Risk_007 | Technical debt risks | 5 | 5 | taking the easy way during SDLC might cause increase in rework cost | Avoid | Conduct rigorous peer reviews and ensure each step is done efficiently before moving to the next step
Issues
ID | Initiator | Probability | Impact | Description | Handling | Actions
Issue_001 | Exams and other cources | 4 | 4 | Team is commited to projects,exams and other courses | Mitigate | Distribute tasks among teams based on previous technical backgrounds to increase productivity and conduct daily meetings to monitor progress

## Release#2
Day | Planned | Consumed | Team Availability |  |  |  | Deliverable | % Completed | Comments
1 | 24 | 0 | 57 |  |  |  | CRS | 0%
2 | 30 | 0 |  |  |  |  | SIQ | 0%
3 | 34 | 0 |  |  |  |  | PMP | 100%
4 | 38 | 0 |  |  |  |  | Risk sheet | 100%
5 | 42 | 7 |  |  |  |  | SRS | 0%
6 | 58 | 37 |  |  |  |  | Testcase draft | 0%
7 | [6 empty] | RTM | 0%
[7 empty] | CMP | 0%
Risks
ID | Topic | Probability | Impact | Description | Handling | Actions
Issues
ID | Initiator | Probability | Impact | Description | Handling | Actions
Issue_001 | team have exams | 5 | 5 | Team is commited to exams | Mitigate | working over time on days after exams

## Release#3
Day | Planned | Consumed | Team Availability |  |  |  | Deliverable | % Completed | Comments | Hours | Done
1 | 24 | 24 | 70 |  |  |  | sprintPlan | 100% | nabil | 3 | 3
2 | 28 | 28 |  |  |  |  | Testcase_ Flight Results | 100% | alaaa | 3 | 3
3 | 38 | 28 |  |  |  |  | Testcase_ Passenger Details | 100% | zahraan | 3 | 3
4 | 46 | 38 |  |  |  |  | Testcase_ Admin Login | 100% | alhussin | 3 | 3 |  |  | Comments | Sum of Hours | Sum of Done
5 | 58 | 46 |  |  |  |  | FlowChart A | 100% | Boda | 3 | 3 |  |  | abdalrahman | 9 | 5
6 | 70 | 70 |  |  |  |  | FlowChart B | 100% | abdalrahman | 3 | 3 |  |  | alaaa | 9 | 5
[7 empty] | SRS Review | 100% | nabil | 3 | 3 |  |  | alhussin | 11 | 7
[7 empty] | testcase review | 100% | nabil | 3 | 3 |  |  | Boda | 3 | 3
[7 empty] | learning _sequence diagram A | 100% | alhussin | 2 | 2 |  |  | nabil | 27 | 19
[7 empty] | learning _sequence diagram B | 100% | zahraan | 2 | 2 |  |  | zahraan | 11 | 7
Risks | [6 empty] | Update wireframe | 100% | nabil | 10 | 10 |  |  | Grand Total | 70 | 46
ID | Topic | Probability | Impact | Description | Handling | Actions | update Siq 1 | 100% | zahraan | 1 | 1
[7 empty] | update Siq 2 | 100% | alhussin | 1 | 1
[7 empty] | update Siq 3 | 100% | alaaa | 1 | 1
[7 empty] | update Siq 4 | 100% | abdalrahman | 1 | 1
[7 empty] | review Siq 1 | 100% | zahraan | 1 | 1
[7 empty] | review Siq 2 | 100% | alhussin | 1 | 1
[7 empty] | review Siq 3 | 100% | alaaa | 1 | 1
[7 empty] | review Siq 4 | 100% | abdalrahman | 1 | 1
[7 empty] | SRS 1 | 100% | alhussin | 2 | 2
[7 empty] | SRS 2 | 100% | abdalrahman | 2 | 2
[7 empty] | SRS 3 | 100% | zahraan | 2 | 2
[7 empty] | SRS 4 | 100% | alaaa | 2 | 2
[7 empty] | SRS v2 review | 100% | nabil | 4 | 4
[7 empty] | Testcase 1 | 100% | alhussin | 2 | 2
[7 empty] | Testcase 2 | 100% | abdalrahman | 2 | 2
Issues | [6 empty] | Testcase 3 | 100% | alaaa | 2 | 2
ID | Initiator | Probability | Impact | Description | Handling | Actions | Testcase 4 | 100% | zahraan | 2 | 2
1 |  | 5 | 5 | Stablization itiration due to lingring issues on main documents of previos releases | Mitigate | reviewing and update all work products from previous itirations | Testcase v2 review | 100% | nabil | 4 | 4
[9 empty] | Sum | 70 | 70
[12 empty] | Day | Planned | Iteam | Comment | Total
[12 empty] | 1 | 3 | sprintPlan | nabil | 24
[13 empty] | 3 | Testcase_ Flight Results | alaaa
[13 empty] | 3 | Testcase_ Passenger Details | zahraan
[13 empty] | 3 | Testcase_ Admin Login | alhussin
[13 empty] | 3 | SRS Review | nabil
[13 empty] | 3 | testcase review | nabil
[13 empty] | 3 | FlowChart A | Boda
[13 empty] | 3 | FlowChart B | abdalrahman
[12 empty] | 2 | 2 | learning _sequence diagram A | alhussin | 4
[13 empty] | 2 | learning _sequence diagram B | zahraan
[12 empty] | 3 | 10 | Update wireframe | nabil | 10
[12 empty] | 4 | 1 | update Siq 1 | zahraan | 8
[13 empty] | 1 | update Siq 2 | alhussin
[13 empty] | 1 | update Siq 3 | alaaa
[13 empty] | 1 | update Siq 4 | abdalrahman
[13 empty] | 1 | review Siq 1 | zahraan
[13 empty] | 1 | review Siq 2 | alhussin
[13 empty] | 1 | review Siq 3 | alaaa
[13 empty] | 1 | review Siq 4 | abdalrahman
[12 empty] | 5 | 2 | SRS 1 | alhussin | 12
[13 empty] | 2 | SRS 2 | abdalrahman
[13 empty] | 2 | SRS 3 | zahraan
[13 empty] | 2 | SRS 4 | alaaa
[13 empty] | 4 | SRS v2 review | nabil
[12 empty] | 6 | 2 | Testcase 1 | alhussin | 12
[13 empty] | 2 | Testcase 2 | abdalrahman
[13 empty] | 2 | Testcase 3 | alaaa
[13 empty] | 2 | Testcase 4 | zahraan
[13 empty] | 4 | Testcase v2 review | nabil
[15 empty] | Sum | 70

## Release#4
Day | Planned | Consumed | Team Availability |  |  |  | Deliverable | % Completed | Comments | Hours | Done
1 | 15 | 15 | 50 |  |  |  | sprintPlan | 100% | nabil | 3 | 3
2 | 15 | 15 |  |  |  |  | javaScript learning1 | 100% | alaaa | 3 | 3
3 | 15 | 15 |  |  |  |  | javaScript learning2 | 100% | zahraan | 3 | 3
4 | 15 | 15 |  |  |  |  | javaScript learning3 | 100% | alhussin | 3 | 3 |  |  | Comments | Sum of Hours | Sum of Done
5 | 15 | 15 |  |  |  |  | javaScript learning4 | 100% | abdalrahman | 3 | 3 |  |  | abdalrahman | 11 | 11
6 | 50 | 50 |  |  |  |  | javaScript learning5 | 100% | nabil | 3 | 3 |  |  | alaaa | 11 | 11
[7 empty] | css/html learning 1 | 100% | alhussin | 3 | 3 |  |  | alhussin | 11 | 11
[7 empty] | css/html learning 2 | 100% | zahraan | 3 | 3 |  |  | nabil | 6 | 6
[7 empty] | nodeJs/ExpressJS learning1 | 100% | alaaa | 8 | 8 |  |  | zahraan | 11 | 11
[7 empty] | nodeJs/ExpressJS learning2 | 100% | abdalrahman | 8 | 8 |  |  | Grand Total | 50 | 50
Risks | [6 empty] | frontend development 1 | 100% | alhussin | 5 | 5
ID | Topic | Probability | Impact | Description | Handling | Actions | frontend development 2 | 100% | zahraan | 5 | 5
Issues
ID | Initiator | Probability | Impact | Description | Handling | Actions
1 |  | 5 | 5 | lack of team members due to illnes | Accept
[9 empty] | Sum | 50 | 50
[12 empty] | Day | Planned | Iteam | Comment | Total
[12 empty] | 1 | 3 | sprintPlan | nabil | 15
[13 empty] | 3 | javaScript learning1 | alaaa
[13 empty] | 3 | javaScript learning2 | zahraan
[13 empty] | 3 | javaScript learning3 | alhussin
[13 empty] | 3 | javaScript learning4 | abdalrahman
[12 empty] | 2 | 3 | css/html learning 1 | alhussin | 6
[13 empty] | 3 | css/html learning 1 | alhussin
[12 empty] | 3 | #N/A |  | #N/A | 0
[12 empty] | 4 | #N/A |  | #N/A | 0
[13 empty] | #N/A |  | #N/A
[13 empty] | #N/A |  | #N/A
[13 empty] | #N/A |  | #N/A
[13 empty] | #N/A |  | #N/A
[13 empty] | #N/A |  | #N/A
[13 empty] | #N/A |  | #N/A
[13 empty] | #N/A |  | #N/A
[12 empty] | 5 | #N/A |  | #N/A | 0
[13 empty] | #N/A |  | #N/A
[13 empty] | #N/A |  | #N/A
[13 empty] | #N/A |  | #N/A
[13 empty] | #N/A |  | #N/A
[12 empty] | 6 | 8 | nodeJs/ExpressJS learning1 | alaaa | 29
[13 empty] | 8 | nodeJs/ExpressJS learning2 | abdalrahman
[13 empty] | 5 | frontend development 1 | alhussin
[13 empty] | 5 | frontend development 2 | zahraan
[13 empty] | 3 | javaScript learning5 | nabil
[15 empty] | Sum | 50